ABC Contracting

317 Bayside Rd.

Manteo, NC USA 27954

Phone: (555) 123-4567

Email: info@abccontracting.com

Date: June 24, 2024

To: Bike Mechanics SkyPort (BKM)

Attn: Facilities Management Department

Subject: Proposal for Restroom Renovation at Gate 10

Dear BKM Facilities Management Team,

We are pleased to submit our proposal for the renovation of the restrooms adjacent to Gate 10 at Bike Mechanics SkyPort. ABC Contracting specializes in airport facility upgrades, and we are confident in our ability to deliver exceptional results within your specified parameters.

Project Scope:

- Replace 30 sinks

- Replace 40 toilet fixtures

- All work to be conducted between 9 PM and 6 AM

Proposed Timeline:

We estimate the project will take 12 working nights to complete, ensuring efficient installation, thorough testing, and rigorous quality checks.

Detailed Breakdown:

1. Preparatory Work (1 night):

- Site assessment and final measurements

- Material and equipment staging

- Installation of temporary facilities

2. Sink Replacements (4 nights):

- Removal and disposal of existing sinks

- Installation of 30 new sinks (7-8 per night)

- Plumbing connections and initial testing

3. Toilet Fixture Replacements (5 nights):

- Removal and disposal of existing fixtures

- Installation of 40 new toilet fixtures (8 per night)

- Plumbing connections and initial testing

4. Finishing Work (2 nights):

- Final adjustments and quality assurance tests

- Deep cleaning and area restoration

- Final walkthrough and handover

Materials:

- 30 commercial-grade sinks (Brand: AquaPro Commercial Series)

- 40 low-flow toilet fixtures (Brand: EcoFlush Elite)

- Premium plumbing supplies and fixtures

- Specialized airport-grade tools and equipment

Labor:

- 1 Senior Project Manager

- 5 Licensed Plumbers

- 3 Skilled Laborers

- 1 Dedicated Quality Assurance Specialist

Safety and Compliance:

- Strict adherence to all airport security protocols

- Comprehensive insurance and bonding

- Full compliance with local, state, and federal regulations

Quality Assurance:

- Continuous monitoring by our on-site QA Specialist

- Nightly progress reports and quality checks

- Final inspection with BKM representatives

All-In Price: $325,750

This comprehensive price includes all labor, premium materials, specialized equipment, necessary permits, and an extended 3-year warranty on all installed fixtures and workmanship.

Price Breakdown:

- Labor: $156,000

- Materials: $132,500

- Equipment and Tools: $18,250

- Permits and Fees: $7,000

- Overhead and Profit: $12,000

Payment Terms:

- 25% due upon contract signing

- 50% due at project mid-point

- 25% due upon satisfactory project completion and final inspection

Value-Added Services:

- 24/7 emergency support for 30 days post-completion

- Complimentary 6-month and 1-year maintenance check-ups

- Training session for BKM maintenance staff on new fixtures

ABC Contracting is enthusiastic about the opportunity to contribute to the enhancement of Bike Mechanics SkyPort. Our team of experts is prepared to commence work within 10 days of contract approval, ensuring minimal disruption to your operations.

We are committed to delivering a superior renovation that will improve the passenger experience and optimize resource efficiency. If you require any clarifications or have additional questions, please don't hesitate to reach out.

We look forward to the possibility of partnering with BKM on this crucial facility upgrade.

Sincerely,

Sarah Smith

Senior Project Director, ABC Contracting